## Sprint 1 (April 21-25)
ITSC-3155 Software Engineering
Sprint 1 Backlog (April 21-25)
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
#1: Guest Checkout | 8 | All | 14 | 4 | 4 | 3 | 3 | 0 | 0 | To Do
Design Order DB Schema |  | All | 6 | 4 | 2 | 0 | 0 | 0 | 0 | Done | 6
Implement Order Endpoints |  | All | 8 | 0 | 2 | 3 | 3 | 0 | 0 | Done | 8
#2: Menu Filtering | 13 | All | 10 | 0 | 2 | 4 | 2 | 2 | 0 | To Do
Create Category Filters |  | All | 6 | 0 | 2 | 2 | 2 | 0 | 0 | Done | 6
Implement GET |  | All | 4 | 0 | 0 | 2 | 0 | 2 | 0 | Done | 4
#3: API & DB Core Setup | 5 | All | 12 | 6 | 4 | 2 | 0 | 0 | 0 | To Do
Connect FastAPI to MySQL |  | All | 6 | 4 | 2 | 0 | 0 | 0 | 0 | Done | 6
Define Base Models & Auth |  | All | 6 | 2 | 2 | 2 | 0 | 0 | 0 | Done | 6
TOTAL |  |  | 36 | 10 | 10 | 9 | 5 | 2 | 0 |  | 14

## Sprint 2 (April 28- May 2)
ITSC-3155 Software Engineering
Sprint 2 Backlog (April 21- May 2)
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
#1: Customer Perspectives | 13 | All | 15 | 5 | 5 | 3 | 2 | 0 | 0 | To Do
Write SQL for 7 Customer Qs |  | All | 10 | 3 | 4 | 3 | 0 | 0 | 0 | Done | 10
Map Customer Endpoints in FastAPI |  | All | 5 | 2 | 1 | 0 | 2 | 0 | 0 | Done | 5
#2: Staff Perspectives | 13 | All | 15 | 0 | 4 | 5 | 4 | 2 | 0 | To Do
Write SQL for 7 Staff Qs |  | All | 10 | 0 | 2 | 3 | 3 | 2 | 0 | Done | 10
Map Staff Endpoints in FastAPI |  | All | 5 | 0 | 2 | 2 | 1 | 0 | 0 | Done | 5
#3: QA & Final Presentation | 5 | All | 12 | 0 | 0 | 2 | 5 | 5 | 0 | To Do
Implement Unit Tests (pytest) |  | All | 6 | 0 | 0 | 2 | 2 | 2 | 0 | Done | 6
Record 5 min Demo |  | All | 6 | 0 | 0 | 0 | 3 | 3 | 0 | Done | 6
TOTAL |  |  | 42 | 5 | 9 | 10 | 11 | 7 | 0 |  | 14